## Slide 1: Gopher Canyon Emergency Pipe Project Update
Esa Lagunas: 1/28/2025

## Slide 2: Background
7/26 Main break
8/6 Presented to E&O

## Slide 5: Background
8/27 Board approved $600K
  Emergency Paving
  Emergency Pipe Project
  Ordered pipe and fittings
9/26 Pipe Arrived

## Slide 6: 9/30 Started Installing Pipe
12-inch CML&C pipe
Upsizing from 8-inch
4 days to install 350-feet

## Slide 7: Update
10/3 Finished installing pipe
10/7 Pipe Testing (3 Days)
  Pressure testing
  High-Chlorine
  Flushing
  Bac-T samples

## Slide 8: 10/14 Tie-in Eastside (2 working days)

## Slide 9: 10/21 Tie-in Westside (2 working days)

## Slide 10: Paving Completed 12/3

## Slide 11: Slurry and Striping 12/10 – 12/12

## Slide 12
Main Break July 26, 2024
Presented to E&O August 6, 2024
Board Approved August 27, 2024
10/3 Finished Installing pipe
Paving December 2024
Started Installing Pipe September 30, 2024
Tie in East 10/14
Tie in West 10/21

## Slide 13: Cost Summary
$97,500 Paving
$74,565 RMWD Labor
$63,738 Pipe & Parts
$19,207 Equip. Rental
$10,301 Traffic Control
$9,276 Backfill Material
______________________
$274,587 Total Project Cost
Chart: 
| RMWD Labor | Pipe & Parts | Paving | Traffic Control | Backfill Material | Equipment Rental
 | 74564.96 | 63738.01 | 97500 | 10300.5 | 9275.98 | 19207.24

## Slide 14: Questions?