## Slide 1: Gopher Canyon Emergency Pipe Project Update
Esa Lagunas: 11/5/2024

## Slide 2: Background
7/26 Main break
8/6 Presented to E&O

## Slide 3: Background
8/27 Board approved $400K
  Emergency Paving
  Emergency Pipe Project
  Ordered pipe and fittings
9/26 Pipe Arrived

## Slide 4: 9/30 Started Installing Pipe
12-inch CML&C pipe
Upsizing from 8-inch
4 days to install 350-feet

## Slide 5: Update
10/3 Finished installing pipe
10/7 Pipe Testing (3 Days)
  Pressure testing
  High-Chlorine
  Flushing
  Bac-T samples

## Slide 6: 10/14 Tie-in Eastside (2 working days)

## Slide 7: 10/21 Tie-in Westside (2 working days)

## Slide 8: Paving Coming Soon

## Slide 11: Questions?